## Project Planner
PAR Gantt Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 22 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | JULY |  |  | w1 |  |  |  |  | AUGUST |  |  | w2 | [5 empty] | w3 | [6 empty] | w4 | [6 empty] | w5 | [6 empty] | w6 | SEPTEMBER | [5 empty] | vac | [6 empty] | w7 | [6 empty] | w8 | [6 empty] | w9 |  |  | OCTOBER |  |  |  | w10 | [6 empty] | w11 | [6 empty] | w12 | [6 empty] | w13 | [5 empty] | NOV
 | time axis 2023-07-24 to 2023-11-01
 | time axis 2023-07-24 to 2023-11-01
 | time axis 2023-07-24 to 2023-11-01
Literature Review | 1 | 12 | 1 | 15 | 75%
Problem statement, scope and limitations, plan of dev. | 7 | 5 | 8 | 2 | 100%
Diode selection | 11 | 7 | 16 |  | 0%
Design requirements and specifications | 11 | 7 | 16 |  | 0%
Sensor node design | 15 | 10 |  |  | 0%
Order components/sensors | 18 | 7 |  |  | 0%
Testing rig design | 25 | 7 |  |  | 0%
Build testing rig | 29 | 21 |  |  | 0%
Build sensor node | 43 | 7 |  |  | 0%
Test sensor node | 50 | 14 |  |  | 0%
Compare results to PAR sensor | 50 | 14 |  |  | 0%
Sensor calibration | 57 | 14 |  |  | 0%
Results and discussion | 67 | 11 |  |  | 0%
Report writing | 71 | 28 |  |  | 0%
Poster design | 94 | 7 |  |  | 0%
Final presentation | 101 | 1 |  |  | 0%
Activity 17 |  |  |  |  | 0%
Activity 18 |  |  |  |  | 0%
Activity 19 |  |  |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%